## Western
Montana Western Region Hazard Mitigation Plans [HMP Status Tracker]
County or Tribe | MT DES Contractor | MT DES Mitigation | County or Tribe | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | State Review | MT DES Mitigation | Federal Review | FEMA | County or Tribe | FEMA
Annex | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to Counties/Tribes? | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to MT DES Contractor? | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to contractors? | Completed Review? | Sent updated plan & PRT to FEMA? | Completed Review? | APA Status? | Locally Adopted? | Approval Letter? | #VALUE!
Beaverhead County | 2024-07-02 | 2024-07-02 | 2024-08-13 | 2024-08-13 | 2024-10-08 | 2024-10-11 | 2025-01-08 | 2025-01-09 | 2025-02-19 | 2025-02-19 | Beaverhead County: 08/04/2025 City of Dillon: 08/20/2025 Town of Lima: 09/02/2025 | Beaverhead County: 08/08/2025 City of Dillon: 09/05/2025 Town of Lima: 09/05/2025
Broadwater County | 2024-07-02 | 2024-07-02 | 2024-09-19 | 2024-09-20 | 2024-10-08 | 2024-10-11 | 2025-01-08 | 2025-01-09 | 2025-02-19 | 2025-02-19 | Broadwater County: 06/04/2025 City of Townsend: 06/17/2025 | Broadwater County: 06/06/2025 City of Townsend: 06/27/2025
Butte-Silver Bow County | 2024-07-02 | 2024-07-02 | 2024-07-18 | 2024-07-19 | 07/24/24 & 01/13/25 | 10/11/24 & 01/13/25 | 01/08/25 & 01/27/25 | 01/08/25 & 01/31/25 | 2025-04-15 | 2025-04-15 | Butte-Silver Bow County: 07/21/2025 Town of Walkerville: 05/19/2025 | Butte-Silver Bow County: 08/01/2025 Town of Walkerville: 08/01/2025
Confederated Salish & Kootenai Tribe (CSKT) | 2024-07-05 | 2024-07-08 | 2024-10-07 | 2024-10-07 | 10/8/2024 & 11/05/2024 | 2024-10-17 | 2025-01-08 | 2025-01-09 | 2025-02-12 | 2025-02-12 | CSKT: 07/31/2025 | CSKT: 08/12/2025
Flathead County | 2024-07-02 | 2024-07-02 | 07/15/24 & 8/8/24 & 12/11/24 | 8/12/2024 & 12/16/24 | 10/8/24 & 12/04/24 | 10/11/24 & 12/04/24 | 2025-01-08 | 2025-01-09 | 2025-02-19 | 2025-02-19 | Flathead County: 03/27/25 City of Columbia Falls: 03/03/2025 City of Kalispell: 10/20/2025 City of Whitefish: 03/17/25 | Flathead County: 04/21/2025 City of Columbia Falls: 04/21/2025 City of Kalispell: 11/17/2025 City of Whitefish: 04/21/2025 | *Note: "RN&OD" references Revision Needs & Other Documention.
Jefferson County | 2024-07-02 | 2024-07-02 | 2024-08-11 | 2024-08-12 | 10/16/24 & 12/13/24 & 01/24/25 | 10/17/24 & 12/2/24 & 12/20/24 & 01/24/25 | 12/6/24 & 01/08/25 & 01/27/25 | 2025-01-31 | 2025-04-15 | 2025-04-15 | Jefferson County: 07/01/2025 City of Boulder: 08/18/2025 Town of Whitehall: 10/20/2025 | Jefferson County: 07/03/2025 City of Boulder: 08/29/2025 Town of Whitehall: 11/17/2025
Lake County | 2024-07-02 | 2024-07-02 | 2024-07-22 | 2024-07-22 | 2024-10-11 | 2024-10-11 | 2025-01-08 | 1/9/25 & 02/21/25 | 2025-02-24 | 2025-02-24 | Lake County: 04/14/2025 City of Polson: 04/08/2025 City of Ronan: 03/26/25 Town of St.Ignatius: 03/04/25 | Lake County: 05/02/2025 City of Polson: 04/21/2025 City of Ronan: 04/21/2025 Town of St.Ignatius: 04/21/2025
Lewis and Clark County | 2024-07-02 | 2024-07-02 | 8/5/2024 & L&C sent Revisions on 10/21 during MEMA Breifing | 2024-08-05 | 2025-01-23 | 2025-01-24 | State Review Revisions Issued 01/27/25 & State Review passed 02/04/25 | 2025-02-04 | 2025-02-25 | 2025-02-25 | Lewis & Clark County: 06/03/2025 City of Helena: 08/18/2025 City of East Helena: 08/19/2025 | Lewis & Clark County: 06/06/2025 City of Helena: 08/29/2025 City of East Helena: 08/29/2025
Lincoln County | 2024-07-02 | 2024-07-02 | 2024-08-14 | 2024-08-15 | 2024-10-08 | 2024-10-09 | 2024-10-16 | 2024-10-25 | 10/25/24 & 11/21/2024 | 2024-11-22 | Lincoln County: 11/13/2024 City of Libby: 05/05/2025 Town of Troy: 11/03/2025 Town of Eureka: 06/09/2025 Town of Rexford: 10/20/2025 | Lincoln County: 11/21/24 City of Libby: 09/29/2025 Town of Troy: 11/17/2025 Town of Eureka: 06/13/25 Town of Rexford: 11/17/2025
Madison County | 2024-07-02 | 2024-07-02 | 2024-08-15 | 2024-08-15 | 10/16/2024 & 01/30/25 | 10/17/2024 & 01/30/25 | 01/08/25 & 01/27/25 & State Review passed 02/04/25 | 2024-02-04 | 2025-04-15 | 2025-04-15 | Madison County: 06/03/2025 Town of Ennis: 10/09/2025 Town of Sheridan: 10/14/2025 Town of Twin Bridges: 10/29/2025 Town of Virginia City: pending | Madison County: 06/06/2025 Town of Ennis: 11/17/2025 Town of Sheridan: 11/17/2025 Town of Twin Bridges: 11/20/2025 Town of Virginia City: pending
Meagher County | 2024-07-02 | 2024-07-02 | - | - | 2024-10-16 | 2024-10-17 | 2025-01-08 | 2025-01-09 | 2025-02-19 | 2025-02-19 | Meagher County: 03/18/25 City of White Sulphur Springs: 11/03/25 | Meagher County: 04/21/2025 City of White Sulphur Springs: 11/17/2025
Mineral County | 2024-07-02 | 2024-07-02 | 2024-10-07 | 2024-10-10 | 2024-10-16 | 2024-10-17 | 2025-01-08 | 2025-01-09 | 2025-02-19 | 2025-02-19 | Mineral County: 04/03/2025 Town of Alberton: 09/17/2025 Town of Superior: 09/08/2025 | Mineral County: 04/21/2025 Town of Alberton: 09/19/2025 Town of Superior: 09/15/2025
Park County | 2024-07-02 | 2024-07-02 | 2024-08-08 | 2024-08-12 | 2024-10-21 | 2024-10-22 | 2025-01-08 | 1/9/2025 & 02/21/25 | Required Revisions issued 02/19/25 & Final Review 2/24/2025 | 2025-02-24 | Park County: 05/20/2025 City of Livingston: 02/04/25 Town of Clyde Park: 06/09/2025 | Park County: 05/23/25 City of Livingston: 06/06/2025 Town of Clyde Park: 08/29/2025
Powell County | 2024-07-02 | 07/03/24 & 08/13/24 | 2024-10-07 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-15 | 2024-10-25 | 10/25/24 & 11/21/2024 | 2024-11-22 | Powell County: 11/23/24 City of Deer Lodge: 12/16/24 | Powell County: 11/21/2024 City of Deer Lodge: 01/08/2025
Ravalli County | 2024-07-02 | 2024-07-02 | 2024-07-15 | 2024-07-15 | 2024-10-21 | 2024-10-22 | 2025-01-08 | 2025-01-09 | 2025-02-24 | 2025-02-24 | Ravalli County: 03/10/25 City of Hamilton: 11/04/2025 Town of Darby: 10/28/2025 Town of Pinesdale: 11/17/2025 Town of Stevensville: 11/13/2025 | Ravalli County: 04/21/2025 City of Hamilton: 11/17/2025 Town of Darby: 11/17/2025 Town of Pinesdale: 11/20/2025 Town of Stevensville: 11/17/2025
Sanders County | 2024-07-02 | 2024-07-02 | 2024-07-16 | 2024-07-16 | 2024-10-21 | 2024-10-22 | 2025-01-08 | 2025-01-09 | 2025-02-19 | 2025-02-19 | Sanders County: 02/27/25 City of Thompson Falls: 03/10/25 Town of Hot Springs: 03/04/25 Town of Plains: 03/12/25 | Sanders County: 04/21/2025 City of Thompson Falls: 04/21/2025 Town of Hot Springs: 04/21/2025 Town of Plains: 04/21/2025
County or Tribe | MT DES Contractor | MT DES Mitigation | County or Tribe | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | State Review | MT DES Mitigation | Federal Review | FEMA | County or Tribe | FEMA
Addendum | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to Counties/Tribes? | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to MT DES Contractor? | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to contractor? | Completed Review? | Sent updated plan & PRT to FEMA? | Completed Review? | APA Status? | Locally Adopted? | Approval Letter?
Granite County | 2024-07-02 | 2024-07-02 | 2024-07-17 | 2024-07-18 | 2024-10-23 | 2024-10-25 | 2025-01-08 | 2025-01-09 | 2025-02-19 | 2025-02-19 | Granite County: 03/04/25 Town of Drummond: 03/18/25 Town of Philipsburg: 03/18/25 | Granite County: 04/21/2025 Town of Drummond: 04/21/2025 Town of Philipsburg: 04/21/2025
Sweet Grass County | 2024-07-02 | 2024-07-02 | 2024-07-16 | 2024-07-16 | 2024-10-23 | 2024-10-25 | 2025-01-08 | 2025-01-09 | 2025-02-19 | 2025-02-19 | Sweet Grass County: 03/11/25 City of Big Timber: 03/17/25 | Sweet Grass County: 4/21/2025 City of Big Timber: 4/21/2025
Region | MT DES Contractor | MT DES Mitigation | Region | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | State Review | MT DES Mitigation | Federal Review | FEMA | County or Tribe | FEMA
| - | - | - | Sent RN&OD to MT DES Contractor? | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to Contractor? | Completed Review? | Sent updated plan & PRT to FEMA? | Completed Review? | APA Status? | Locally Adopted? | Approval Letter?
Western Region Base Plan + Appendicies | - | - | - | - | 07/24/24 & 08/15/24 & 10/29/24 | 8/16/2024 & 10/29/24 | 2024-09-03 | 2024-10-29 | 2024-11-21 | 2024-11-22 | Ongoing | 2024-11-21

## Central
Montana Central Region Hazard Mitigation Plans [HMP Status Tracker]
County or Tribe | MT DES Contractor | MT DES Mitigation | County or Tribe | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | FEMA | FEMA | County or Tribe | FEMA
Annexes | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to Counties/Tribes? | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to MT DES Contractor? | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to FEMA? | Completed Review? | APA Status? | Locally Adopted? | Approval Letter?
Blaine County | 2024-05-23 | 2024-05-23 | 07/15/24 & 08/08/24 | 07/15/24 & 08/08/24 | 07/11/24 & 08/13/24 | 2024-08-16 | 2024-08-29 | 2024-09-12 | Blaine County: 11/04/24 City of Chinook: 01/14/25 City of Harlem: 01/13/25 | Blaine County: 2/10/2025 City of Chinook: 2/10/2025 City of Harlem: 2/10/2025 | #VALUE!
Blackfeet Nation | 2024-05-19 | 2024-05-24 | 2024-08-26 | 2024-08-26 | 7/15/24 & 08/12/24 & 09/13/24 | 2024-09-13 | 2024-09-17 | 2024-09-17 | Blackfeet Nation: 02/07/25 | Blackfeet Nation: 2/12/2025
Cascade County | 2024-05-22 | 2024-05-23 | 2024-06-10 | 2024-06-10 | 07/03/24 & 07/10/24 & 09/13/24 | 07/03/24 & 08/08/24 & 09/13/24 | 08/29/24 & 09/17/24 | 2024-09-17 | Cascade County: 11/26/24 City of Great Falls: 03/05/2025 Town of Belt: 02/05/25 Town of Cascade: 01/09/25 | Cascade County: 12/6/2024 City of Great Falls: 04/25/2025 Town of Belt: 2/14/2025 Town of Cascade: 1/16/2025
Chouteau County | 05/23/24 & 06/13/24 | 2024-05-24 | 2024-06-26 | 2024-06-26 | 2024-07-12 | 2024-08-08 | 2024-08-29 | 2024-09-12 | Chouteau County: 11/18/24 City of Fort Benton: 11/04/24 Town of Big Sandy: 02/13/25 | Chouteau County: 11/22/2024 City of Fort Benton: 11/22/2024 Town of Big Sandy: 2/21/2025
Fergus County | 2024-05-23 | 2024-05-23 | 2024-05-29 | 2024-05-29 | 07/03/24 & 07/10/24 | 07/03/24 & 08/08/24 | 2024-08-29 | 2024-09-12 | Fergus County: 10/10/24 City of Lewistown: 10/07/24 Town of Denton: 11/18/24 Town of Grass Range: 10/14/24 Town of Moore: 11/07/24 Town of Winifred: 10/08/24 | Fergus County: 11/22/2024 City of Lewistown: 11/22/2024 Town of Denton: 11/22/2024 Town of Grass Range: 11/22/2024 Town of Moore: 11/22/2024 Town of Winifred: 11/22/2024 | *Note: "RN&OD" references Revision Needs & Other Documention.
Glacier County | 05/24/24 & 06/13/24 | 2024-06-14 | 2024-07-10 | 2024-07-10 | 2024-07-12 | 2024-07-15 | 2024-08-29 | 2024-09-12 | Glacier County: 10/10/2024 City of Cut Bank: 07/21/2025 | Glacier County: 10/11/24 City of Cut Bank: 07/25/2025
Hill County | 2024-05-22 | 2024-05-23 | 07/18/24 & 08/16/24 | 07/19/24 & 08/16/24 | 07/12/24 & 07/19/24 & 08/22/24 | 2024-08-23 | 2024-08-29 | 2024-09-12 | Hill County: 9/26/2024 City of Havre: 12/02/24 Town of Hingham: 06/12/25 | Hill County: 10/11/24 City of Havre: 05/27/25 Town of Hingham: 06/13/25
Judith Basin County | 2024-05-23 | 2024-06-03 | 2024-06-04 | 2024-06-04 | 07/03/24 & 07/10/24 & 09/13/24 | 07/03/24 & 08/08/24 & 09/13/24 | 08/29/24 & 09/17/24 | Partial APA 09/12 & Full APA 09/17 | Judith Basin County: 11/20/24 Town of Hobson: 05/21/2025 Town of Stanford: 12/09/24 | Judith Basin County: 2/14/2025 Town of Hobson: 06/06/25 Town of Stanford: 2/14/2025
Liberty County | 2024-05-19 | 2024-05-20 | 06/26/24 & 07/09/24 & 08/27/24 | 06/26/24 & 7/9/24 & 8/27/24 | 07/12/24 & 09/13/24 | 2024-09-13 | 2024-09-17 | 2024-09-17 | Liberty County: 10/15/24 Town of Chester: 12/10/24 | Liberty County: 10/15/24 Town of Chester: 12/13/24
Petroleum County | 2024-05-30 | 2024-07-02 | 2024-07-11 | 07/11/24 & 08/05/24 | 07/12/24 & 08/09/24 & 09/13/24 | 8/12/2024 & 09/13/24 | 08/29/24 & 09/17/24 | 2024-09-17 | Petroleum County: 09/19/24 Town of Winnet: 06/11/25 | Petroleum County: 10/11/24 Town of Winnet: 06/13/25
Phillips County | 2024-05-19 | 2024-05-21 | 2024-07-10 | 2024-07-10 | 2024-07-11 | 2024-07-15 | 2024-08-29 | 2024-09-12 | Phillips County: 10/23/24 City of Malta: 10/22/24 Town of Saco: 11/13/24 | Phillips County: 12/06/24 City of Malta: 12/06/24 Town of Saco: 11/22/24
Pondera County | 2024-05-19 | 2024-05-21 | 2024-05-31 | 2024-05-31 | 07/03/24 & 07/10/24 | 07/03/24 & 08/08/24 | 2024-08-29 | 2024-09-12 | Pondera County: 10/09/24 City of Conrad: 10/10/24 Town of Valier: Opted Out | Pondera County: 10/11/2024 City of Conrad: 10/11/2024 Town of Valier: 10/11/2024 (Opted Out)
Rocky Boy/Chippewa Cree | 2024-05-30 | 2024-06-12 | 2024-07-26 | 2024-07-26 | 7/29/2024 & 09/13/24 | 8/8/2024 & 09/13/24 | 08/29/24 & 09/17/24 | 2024-09-17 | Rocky Boy/Chippewa Cree: 10/10/24 | Rocky Boy/Chippewa Cree: 12/20/2024
Toole County | 2024-05-19 | 2024-05-20 | 6/27/24 & 07/01/24, & 07/01/24 | 2024-07-10 | 2024-07-11 | 2024-07-15 | 2024-08-29 | 2024-09-12 | Toole County: 11/07/24 Town of Kevin: 10/09/24 City of Shelby: 11/04/24 Town of Sunburst: 10/15/24 | Toole County: 11/22/2024 Town of Kevin: 11/22/2024 City of Shelby: 11/22/2024 Town of Sunburst: 11/22/2024
County or Tribe | MT DES Contractor | MT DES Mitigation | County or Tribe | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | FEMA | FEMA | County or Tribe | FEMA
Addendums | - | - | - | - | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to FEMA? | Completed Review? | APA Status? | Locally Adopted? | Approval Letter?
Teton County | n/a | n/a | 2024-09-23 | 2024-10-01 | 7/11/24 & 09/13/24 & 11/1/24 | 7/15/2024 & 09/13/24 | 08/29/24 & 09/17/24 | 2024-09-17 | Teton County: 12/19/24 City of Choteau: 12/17/24 Town of Dutton: 02/03/25 Town of Fairfield: 01/08/25 | Teton County: 1/10/2025 City of Choteau: 1/10/2025 Town of Dutton: 04/25/2025 Town of Fairfield: 1/10/2025
Region | MT DES Contractor | MT DES Mitigation | Region | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | FEMA | FEMA | County or Tribe | FEMA
| - | - | - | - | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to FEMA? | Completed Review? | APA Status? | Locally Adopted? | Approval Letter?
Central Region Base Plan + Appendicies | - | - | - | - | 07/03/24 & 09/09/24 | 07/03/24 & 09/10/24 | 08/29/24 & 09/12/24 | 2024-09-17 | Ongoing | 2024-10-11
.

## Eastern
Montana Eastern Region Hazard Mitigation Plans [HMP Status Tracker]
County or Tribe | MT DES Contractor | MT DES Mitigation | County or Tribe | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | State Review | MT DES Mitigation | Federal Review | Participating Jurisdiction | FEMA
Annexes | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to Counties/Tribes? | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to MT DES Contractor? | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to contractors? | Completed Review? | Sent final plan & PRT to FEMA? | APA Status issued? | Locally Adopted? | Approval Letter?
Carbon County | 2024-05-17 | 05/29/24 | 2024-07-02 | 2024-07-03 | 2024-12-06 | 2024-12-09 | 2025-01-15 | 2025-01-16 | Federal Review complete 02/26/25 | Carbon County: 03/18/25 City of Red Lodge: 04/08/25 Town of Bearcreek: 04/03/25 Town of Bridger: 07/08/25 Town of Fromberg: 06/12/25 Town of Joliet: 03/24/25 | Carbon County: 04/17/25 City of Red Lodge: 05/07/25 Town of Bearcreek: 05/07/25 Town of Bridger: 09/05/25 Town of Fromberg: 06/20/25 Town of Joliet: 05/07/25 | #VALUE!
Crow Tribe | 2024-06-25 | 2024-06-25 | 2024-08-12 | 2024-08-12 | 9/27/2024 & 10/24/24 | 9/27/24 & 10/25/24 & 11/1/24 | 2024-10-08 | 11/01/24 & 11/8/24 | 2024-12-11 | Crow Tribe: 03/04/25 | Crow Tribe: 3/12/2025
Custer County | 2024-05-17 | 2024-05-24 | 2024-05-29 | 05/29/24 & 07/26/24 Joint Review feedback | 07/08/24 & incooperated Joint Review feedback 08/22/24 & additional edits 12/20/24 | 07/08/24 & 08/23/24 & 12/23/24 | 07/21/24 (Joint Review) & 09/03/24 (State Review) & 01/15/25 | 2025-01-16 | Federal Review complete 02/05/25 | Custer County: 03/11/25 City of Miles City: 02/25/25 Town of Ismay: 06/09/25 | Custer County: 04/17/25 City of Miles City: 06/06/25 Town of Ismay: 06/13/25
Daniels County | 2024-05-17 | 2024-05-29 | 06/17/24 & 06/06/24 | 06/17/24 & 06/06/24 | 2024-12-06 | 2024-12-06 | 2024-12-24 | 2024-12-26 | Federal Review Complete 1/22/25, APA Status issued 02/05/25 | Daniels County: 03/03/25 City of Scobey: 03/12/25 Town of Flaxville: 03/10/25 | Daniels County: 04/17/25 City of Scobey: 04/17/25 Town of Flaxville: 04/17/25
Garfield County | 2024-05-17 | 2024-06-04 | 2024-06-24 | 2024-06-24 | 10/30/24 & 12/06/2024 | 11/1/2024 & 12/09/2024 | 11/27/24 & 01/15/25 | 2025-01-16 | Federal Review complete 02/26/25 | Garfield County: 07/02/2025 Town of Jordan: 08/05/2025 | Garfield County: 07/11/25 Town of Jordan: 09/05/2025 | *Note: "RN&OD" references Revision Needs & Other Documention.
Powder River County | 2024-05-17 | 2024-06-05 | 2024-08-28 | 2024-08-28 | 12/6/24 & 12/30/24 | 12/6/24 & 12/26/24 & 12/30/24 | 12/26/24 & 01/15/25 | 2025-01-16 | Federal Review complete 02/26/25 | Powder River County: 09/30/2025 Town of Broadus: 10/07/2025 | Powder River County: 10/10/2025 Town of Broadus: 10/10/2025
Prairie County | 2024-05-17 | 2024-05-25 | 2024-08-29 | 2024-08-30 | 10/28/2024 & 12/06/2024 | 11/1/2024 & 12/09/2024 | 11/27/24 & 01/15/25 | 2025-01-16 | Federal Review complete 02/26/25 | Prairie County: 08/20/2025 Town of Terry: 09/11/2025 | Prairie County: 09/05/2025 Town of Terry: 09/15/2025
Roosevelt County | 2024-05-17 | 2024-05-24 | 2024-06-20 | 2024-06-20 | 12/6/24 & 12/30/24 | 12/6/24 & 12/26/24 & 12/30/24 | 12/26/24 & 01/15/25 | 2025-01-16 | Federal Review complete 02/26/25 | Roosevelt County: 03/04/25 City of Wolf Point: 05/19/25 City of Poplar: 05/13/25 Town of Bainville: 05/12/25 Town of Culbertson: 03/10/25 Town of Froid: 04/14/25 | Roosevelt County: 04/17/25 City of Wolf Point: 06/06/25 City of Poplar: 05/16/25 Town of Bainville: 5/16/25 Town of Culbertson: 04/17/25 Town of Froid: 04/21/25
Sheridan County | 2024-05-17 | 2024-05-29 | 2024-06-25 | 2024-06-25 | 12/6/24 & 12/30/24 | 12/6/24 & 12/26/24 & 12/30/24 | 12/26/24 & 01/15/25 | 2025-01-16 | Federal Review complete 02/26/25 | Sheridan County: 07/23/2025 City of Plentywood: 07/21/2025 Town of Medicine Lake: 09/15/2025 Town of Outlook: 08/12/2025 Town of Westby: 07/14/2025 | Sheridan County: 08/01/2025 City of Plentywood: 08/01/2025 Town of Medicine Lake: 11/17/2025 Town of Outlook: 11/17/2025 Town of Westby: 08/01/2025
Valley County | 2024-05-17 | 2024-05-29 | 2024-06-13 | 2024-06-13 | 12/6/24 & 12/30/24 | 12/6/24 & 12/26/24 & 12/30/24 | 12/26/24 & 01/15/25 | 2025-01-16 | Federal Review complete 02/26/25 | Valley County: 04/23/25 City of Glasgow: 05/08/25 Town of Fort Peck: 05/06/25 Town of Nashua: 05/06/25 Town of Opheim: 05/07/25 | Valley County: 05/28/25 City of Glasgow: 05/28/25 Town of Fort Peck: 05/28/25 Town of Nashua: 05/28/25 Town of Opheim: 05/28/25
Yellowstone County | 2024-05-17 | 6/4/2024 & 09/20/24 | 2024-09-24 | 2024-09-26 | 9/18/24 & 10/24/24 | 10/25/24 & 12/23/24 | 12/18/24 & 01/15/25 | 2025-01-15 | APA Status issued 02/05/25 | Yellowstone County: 03/04/25 City of Billings: 04/14/25 Town of Broadview: pending City of Laurel: 03/11/2025 | Yellowstone County: 04/17/25 City of Billings: 04/25/25 Town of Broadview: - City of Laurel: 07/18/2025
`
County or Tribe | MT DES Contractor | MT DES Mitigation | County or Tribe | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | State Review | MT DES Mitigation | Federal Review | County or Tribe | FEMA
Addendums | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to Counties/Tribes? | Submitted RN&OD to MT DES Mitigation? | Sent RN&OD to MT DES Contractor? | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to contractors? | Completed Review? | Sent final plan & PRT to FEMA? | APA Status issued? | Locally Adopted? | Approval Letter?
Big Horn County | 2024-05-17 | 2024-05-31 | 2024-06-12 | 06/12/24 & 07/26/24 Joint Review Feedback | 10/29/2024 & 01/30/25 | 7/8/2024 & 11/01/2024 | 07/21/24 (Joint Reivew) & 11/27/2024 | 12/20/2024 & 01/30/25 | Federal Review Revisions Issued 01/22/25, APA Status issued 02/05/25 | Big Horn County: 2/20/25 City of Hardin: pending Town of Lodge Grass: pending | Big Horn County: 06/13/25 City of Hardin: pending Town of Lodge Grass: pending
Carter County | 2024-05-17 | 2024-05-28 | 2024-06-03 | 6/3/2024 & 04/02/25 | 12/12/24 & 04/14/25 | 2024-12-17 | 2025-01-23 | 2/10/2025 & 04/14/25 | 2025-04-21 | Carter County: 04/30/2025 Town of Ekalaka: 05/14/2025 | Carter County: 05/06/2025 Town of Ekalaka: 05/16/2025
Dawson County | 2024-05-17 | 2024-05-17 | 08/28/24 & 10/10/24 | 8/30/24 & 10/10/24 & 04/02/25 | 12/13/24 & 04/14/25 | 2024-12-17 | 2025-01-23 | 2/10/2025 & 04/14/25 | 2025-04-21 | Dawson County: 07/01/2025 City of Glendive: 08/19/2025 Town of Richey: 08/12/2025 | Dawson County: 07/11/2025 City of Glendive: 09/05/2025 Town of Richey: 09/05/2025
Fallon County | 2024-05-17 | 2024-05-31 | 2024-09-09 | 2024-09-10 | 2024-12-18 | 2024-12-20 | 2025-01-23 | 2025-02-10 | 2025-04-15 | Fallon County: 05/08/2025 City of Baker: 05/07/25 Town of Plevna: 05/14/25 | Fallon County: 05/16/2025 City of Baker: 05/28/2025 Town of Plevna: 05/28/2025
Golden Valley County | 2024-05-17 | 2024-05-31 | 08/13/24 & 09/24/24 | 8/19/2024 & 09/24/24 | 2024-12-13 | 2024-12-17 | 2025-01-23 | 2025-02-10 | 2025-04-15 | Golden Valley County: 05/06/25 Town of Ryegate: 06/02/25 Town of Lavina: 07/10/25 | Golden Valley County: 05/28/25 Town of Ryegate: 06/13/25 Town of Lavina: 07/18/25
McCone County | 2024-05-17 | 2024-06-04 | 2024-06-10 | 2024-06-10 | 2024-12-16 | 12/20/2024 & resubmitted 02/06/25 | State Review Revisions Issued 01/23/25 & State Review completed 02/10/25 | 2025-02-10 | 2025-04-15 | McCone County: 05/24/2025 Town of Circle: 05/12/25 | McCone County: 06/06/2025 Town of Circle: 05/28/25
Musselshell County | 2024-05-17 | 2024-05-29 | No | 2024-09-13 | 2024-12-12 | 2024-12-17 | 2025-01-23 | 2025-02-10 | 2025-04-15 | Musselshell County: 05/16/2025 Town of Melstone: pending Town of Roundup: 05/19/2025 | Musselshell County: 05/16/2025 Town of Melstone: - Town of Roundup: 06/27/2025
Richland County | 2024-05-17 | 2024-05-31 | 2024-09-03 | 9/3/2024 & 04/02/25 | 12/16/24 & 04/14/25 | 2024-12-17 | 2025-01-23 | 2/10/25 & 04/14/25 | 2025-04-16 | Richland County: 05/30/2025 Town of Fairview: 05/14/2025 Town of Sidney: 06/02/2025 | Richland County: 06/06/25 Town of Fairview: 06/06/25 Town of Sidney: 06/06/2025
Rosebud County | 2024-05-17 | 2024-05-31 | 2024-06-04 | 2024-06-04 | 2024-12-18 | 2024-12-20 | 2025-01-23 | 2025-02-10 | 2025-04-15 | Rosebud County: 05/06/25 City of Colstrip: 11/12/2025 City of Forsyth: 06/09/25 | Rosebud County: 06/06/25 City of Colstrip: sent to FEMA on 12/05/2025 City of Forsyth: 06/13/25
Stillwater County | 2024-05-17 | 2024-05-29 | 2024-10-11 | 2024-10-11 | 10/11/2024 & 01/30/25 | 2024-10-11 | State Review completed on 12/18/2024 | 12/19/2024 & 01/30/25 | Federal Review Revisions Issued 01/22/25, APA Status issued 02/05/25 | Stillwater County: 03/20/2025 Town of Columbus: 06/02/2025 | Stillwater County: 04/21/2025 Town of Columbus: 06/06/2025
Treasure County | 2024-05-17 | 2024-05-28 | 2024-06-24 | 6/24/2024 & 12/13/2024 | 2024-12-13 | 2024-12-17 | 2025-01-23 | 2025-02-10 | 2025-04-15 | Treasure County: 02/04/2025 Town of Hysham: 05/14/2025 | Treasure County: 04/15/2025 Town of Hysham: 05/16/2025
Wibaux County | 2024-05-17 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-12-13 | 12/17/2024 & resubmitted 02/06/25 | State Review Revisions Issued 01/23/25 & State Review completed 02/10/25 | 2025-02-10 | 2025-04-21 | Wibaux County: 04/28/2025 Town of Wibaux: 05/08/2025 | Wibaux County: 05/06/2025 Town of Wibaux: 05/16/2025
Region | MT DES Contractor | MT DES Mitigation | Region | MT DES Mitigation | MT DES Contracor | MT DES Mitigation | State Review | MT DES Mitigation | Federal Review | County or Tribe | FEMA
| - | - | - | Sent RN&OD to MT DES Contractor? | Submitted updated Plans to MT DES Mitigation? | Sent updated Plan & PRT to contractors? | Completed Review? | Sent final plan & PRT to FEMA? | APA Status issued? | Locally Adopted? | Approval Letter?
Eastern Region Base Plan + Appendicies | - | - | - | Joint Review feedback sent on 07/26/24 & 08/06/24 | 07/08/24 & 09/05/24 incooperated Joint Review feedback & 11/12/24 | 7/8/24 & 11/12/24 | 7/21/24 & 11/08/24 & 11/18/24 | 11/1/2024 & 11/18/2024 | - Tribal revisions: none - Tribal APA 12/11/24 - County Revisions Issued: 01/22/25 - County APA issued: 02/05/25 | Ongoing | Pending